## Sheet1
ID | Story | Estimation (hours) | Priority | Sprint When Finished
1 | Implement account table(s) | 4 | 1 | 2
2 | Design account table(s) | 4 | 1 | 2
3 | Get user location with Google Places API | 4 | 1 | 1
4 | Set up API keys | 3 | 1 | 1
5 | Possibly updating to firestore | 15 | 1 | 2
6 | Manager override for clock in/out times | 8 | 2 | 2
7 | Design check-in/check-out system | 6 | 2 | 1
8 | Create an account form (unique usernames) | 4 | 2 | 1
9 | Implement check-in/check-out system on volunteer end | 4 | 2 | 1
10 | Role-based authorization | 6 | 2 | 2
11 | Apply to be a volunteer form | 15 | 2 | 2
12 | Implement check-in/check-out approval system on manager end | 10 | 2 | 2
13 | Page to view volunteer records in-app | 10 | 2 | 1
14 | Request to edit profile form | 12 | 3 | 3
15 | Output daily/weekly logs to excel (user and manager) | 10 | 3 | 3
16 | Establish auto-clock-out | 6 | 3 | N/A
17 | Reset password form | 4 | 3 | 1
18 | Implement profile update approval system on manager end | 10 | 3 | N/A
19 | Replace check-in button with QR code scanner | 20 | 3 | 3
20 | Get live number of volunteers | 10 | 4 | 3
21 | Upload profile pictures | 8 | 4 | 3
22 | Print name badges using iPad at TES | 10 | 4 | 2
23 | Establish auto-clock-in | 6 | 4 | 2
24 | QR Code Generator/Manager | 12 | 4 | 3
25 | Create restricted manager roles (just clock-in/out and just QR code) | 3 | 4 | 3
26 | Resubmit denied application | 1.5 | 4 | 3
27 | Manually create records | 4 | 4 | 3
28 | Manager search clock records by name/date/ethnicity/sex | 14 | 4 | 3
29 | Manager search applications by name | 12 | 3 | 3
30 | Website | 4 | 5 | 3
31 | Test cases | 10 | 3 | 3
32 | Build and submit to app store | 15 | 3 | 3 / In progress